## Sprint plan 4
Sprint Plan 2
Group A
User story | Task | Task assigned to | Estimated effort (Hours) | Priority (scale 1-5; low to high) | Notes
As an user, I want to have a product which data is internally structured as covenient as possible. | Datastructuur Implementeren voor data | Martijn | 4 | 3
As a product owner, I want to have a product vision from the group that creates my product, so we can determine whether what I need/expect is understood. | Product Vision afmaken | Bjorn&Lizzy | 4 | 5
| Product Planning draft maken | Lizzy&Bjorn | 4 | 5
As an user, I want the application to accept and handle txt input files. | Create configuration XML files for specifying the structure of the input files | Adam/Daan | 4 | 5
| Parse file based on xml configuration | Adam/Daan | 6 | 5
| Objectify parsed file into internal structure | Adam/Daan/Martijn | 3 | 3
As a user, I want to be able to use this stand alone program easily. Hopefully with a beautiful interface, which will make interaction with the program a lot easier for me. | Een scripting language opstellen voor instructies | Martijn | 4 | 3
| Design several possible UI | Daan&Lizzy | 3 | 4
| Make skeleton for UI | Daan&Lizzy | 3 | 3
Justification of priorities
The product vision is basis of the project, so we have a clear foundation of what our product will be. And as that is build, we want to be at a stage where we have a working demo. So we can deeper analyse what our customer needs are.