## Sprint plan reflection
Reflection on Iteration #2
Group: A, Health Informatics
User story | Task | Task assigned to | Estimated effort (Hours) | Actual effort (Hours) | Priority (scale 1-5; low to high) | Done | Notes
As an user, I want to have a product which data is internally structured as covenient as possible. | Datastructuur Implementeren voor data | Martijn | 4 | 12 | 3 | done | see problem #2; also familiarizing with the used test libraries took a lot of time
As a product owner, I want to have a product vision from the group that creates my product, so we can determine whether what I need/expect is understood. | Product Vision afmaken | Bjorn&Lizzy | 4 | 4 | 5 | done
| Product Planning draft maken | Lizzy&Bjorn | 4 | 3 | 5 | done
As an user, I want the application to accept and handle txt input files. | Create configuration XML files for specifying the structure of the input files | Adam/Daan | 4 | 2 | 5 | done
| Parse file based on xml configuration | Adam/Daan | 6 | 6 | 5 | almost done | still some bugs
| Objectify parsed file into internal structure | Adam/Daan/Martijn | 3 | 6 | 3 | done
As a user, I want to be able to use this stand alone program easily. Hopefully with a beautiful interface, which will make interaction with the program a lot easier for me. | Een scripting language opstellen voor instructies | Martijn | 4 | 1 | 3 | done | just an initial draft
| Design several possible UI | Daan&Lizzy | 3 | 3 | 4 | done
| Make skeleton for UI | Daan&Lizzy | 3 | 8 | 3 | done
Priority
Main problems encountered
Problem 1: | More than a skeleton was needed for the UI demo
Description | To have something to show for the demo at the end of the week, more than just a sceleton was needed, not being familiar with Swing it took a lot more time than estimated, also having to familiarize with the libraries
Reaction | Next time think about what we would like to show at the end of the week, and adjust the targets to that.
Problem 2: | Travis CI and Maven needed to be configured
Description | Travis CI was not configured to use Maven. Maven's pom.xml did not include certain dependencies that were needed in testing and the checkstyle plugin was not configured.
Reaction | Fixed problems, added dependencies and created configuration.
Adjustments for next sprint plan
Next time think about what we would like to show at the end of the week, and adjust the targets to that.