## Sprint plan 3
Sprint Plan 3
Group A
User story | Task | Task assigned to | Estimated effort (Hours) | Priority (scale 1-5; low to high) | Notes
A User wants an easy way of using the GUI, including easy file selecting and format selecting and output. | Make it possible to drop in files | Daan | 2 | 3
| Make files in drop in block with same format | Daan | 5 | 3
| Cleaning up GUI | Daan/Adam | 4 | 3
As a product owner, I want to have a product vision from the group that creates my product, so we can determine whether what I need/expect is understood. | Product Planning final version maken | Lizzy/Bjorn | 4 | 5
As a product owner, I want to have an emergent architecture design from the group that creates my product, so that I can keep track of the design goals and architecture. | Update emergent architecture design | Martijn | 3 | 4
As a User I want the program to do be able to manipulate the data selected via the GUI | Create mock control module | Bjorn/Lizzy | 5 | 3
| Make calls to parsers | Bjorn/Lizzy | 3 | 4
| Make a toString() for datastructure | Martijn | 2 | 3
| Check with Wenxin if scripting language is understandable | Martijn | 1 | 4
| Integrate parse module | Adam | 8 | 5
| Create minimal output module | Martijn | 8 | 4
Justification of priorities
The product vision is basis of the project, so we have a clear foundation of what our product will be. And as that is build, we want to be at a stage where we have a working demo. So we can deeper analyse what our customer needs are.